## Workplan
Workplan MCH construction in Bossaso
Preliminary construction activities |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September
WBS | Activity | Budget | Directly responsible person | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Construction proper
WBS | Item |  | Directly responsible person
| Site visit to obtain building permits |  | Provider/DS/MHD
| Start of construction |  | Provider
| Joint supervision (Engineer, MHD and Project coor) for construction evolution. |  | Enginer/MHD/DS
| Finalizing the construction |  | Provider
| Preparation Donation ceremony |  | DS/MHD

## BOQ
GRIBLE 2 Health Post
BOQ for the construction of Health Post in Grible 2 Bosaso Bari region
A) BOQ for the construction of Health Post in Grible two Health Post
# | Description of Work | Unit | Quantity | Unit Rate | Total Amount (USD)
Preliminary works
1 | Mobilization of all required tools and machinery on site | LS | 1
1 | FOUNDATION, EXCAVATION & CONSTRUCTION
1 | Excavate pits for 14 column footings (300mm x 300mm x 400mm) as approved by an Engineer. | M3 | 0.045
2 | Excavate the foundation trenches for the walls (400 mm wide and 400 mm deep) as approved by an Engineer. | M3 | 31.84
3 | Lay at the bottom of excavated trenches a 50mm of blinding lean cement concrete in a ratio of 1:4:8 as approved by an Engineer. | M3 | 3.98
4 | Provision and construction of foundation stone wall. all joints between stones should be filled with cement/sand mortar with 1:6 ratio. Minimum height of the foundation wall from the Ground level is 25 cm as approved by an Engineer. | M3 | 59.7
2 | CONCRETE WORKS |  |  |  | 0
1 | Column Footings- Providing and laying of 30 cm thick cement concrete mix ratio (1:2:4) including formwork as directed by Engineer. | M3 | 0.09
2 | Ground beam- Providing and laying of 15 cm thick cement 4y10 with stirrups of y8@25cm c/c and concrete mix ratio (1:2:4) including formwork as directed by the Engineer. | M3 | 11.64 |  | 0
3 | Middle ring beam- Providing and laying of 15 cm thick cement 4y10 with stirrups of y8@25cm c/c and concrete mix ratio (1:2:4) including formwork as directed by the Engineer. | M3 | 8.124
4 | Top ring beam- Providing and laying of 15 cm cement concrete mix ratio with 4y10 with stirrups of y8@25cm c/c and (1:2:4) including formwork as directed by the Engineer. | M3 | 3.828 |  | 0
5 | 30cmx30cm columns- Providing and laying of cement concrete mix ratio (1:2:4) with 4y10 bars with y8 stirrpus @20cm c/c including formwork as directed by the Engineer. | M3 | 4.41
3 | FLOOR CONSTRUCTION |  |  |  | 0
1 | Provide and lay a 400mm thick stone fill up well compacted and levelled as approved by an Engineer. | M3 | 45.5
2 | 10 cm thick plain cement concrete flooring of ratio 1:3:6, floor slab should slope towards verandah as approved by an Engineer. | M3 | 18.2
3 | Construction of door steps with stone masonry including concrete screed. Provide 2 rampa for wheel chairs and hospital beds, the width of the ramp should be 2 M wide. All joints between stones should be filled with cement/sand mortar with 1:6 ratio as approved by an Engineer. | L.M. | 1
4 | BLOCK WALLING |  |  |  | 0
1 | Construction of 20 cm thick hollow concrete block walls with cement/sand mortar 1:4 ratio as approved by an Engineer. | M2 | 565.84
5 | ROOFING WORKS |  |  |  | 0
1 | Supply and fix roofing using prepainted iron corrugated sheets # 30 gauge, with timber roof trusses c/c 1.4m. All the roof trusses should be anchored with 6 mm dia. bars in the concrete roof lintel. Flat metal sheet should be anchored where trusses and purlins meet as approved by an Engineer. | M2 | 182
2 | In all rooms and the covered verandah, provide 4mm plywood false ceilings fixed to roof, 2”x2” timber wood 60cm c/c both ways as approved by an Engineer. | M2 | 156.6
3 | Provide and fix 20cmx2.5cm timber fascia board under all eaves and paint and approved by an Engineer. | L.M. | 1
6 | WINDOWS, DOORS
1 | Supply and install 2 leaf doors (2.1 x1.2) m for delivery room and delivary ward. Doors should be made of 1.2mm steel sheet with 25x25 hallow box frame completed with locks, hinges and painting. Door lock-orginal Safety rim dead lock - 6 turns -Original as approved by an Engineer | No. | 2
2 | Supply and install 1 leaf doors (2.1 x0.9) m for all other rooms. Doors should be made of 1.2mm steel sheet with 25x25 hallow box frame completed with locks, hinges and painting. Door lock-orginal Safety rim dead lock - 6 turns -Original as approved by an Engineer | No. | 5
3 | Supply and install 1 leaf doors (2.1 x0.7) m for delivery room latrine. Doors should be made of aluminium frame with non transparent glass completed with locks and hinges. Door lock-should be from both inside and outside as approved by an Engineer | No. | 1
4 | Supply and install 2 leafs steel windows, each leaf should be divided into 2 sections vertically which can be openable with external security mesh, (1.2 x1.2) m. windows should be 1.2mm steel sheet with 25x25 hallow box frame including locks, hinges and painting as approved by an Engineer. | No. | 8 |  | 0
5 | Supply and install 2 leafs steel window for delivery room latrine, it should be openable with external security mesh, (0.6 x0.6)m. windows should be 1.2mm steel sheet with 25x25 hallow box frame including locks, hinges and painting as approved by an Engineer. | No. | 1
6 | Supply and fix steel door (2.5m width and 2.5cm height) for the paramer wall fixed with 45x45cm columns including casting of the two columns with 4y14 bars with y8 stirrups of 20cm c/c for fixing the entrance gate and laying of concrete slope with 30% slope for cars entering from the front gate. | Pcs | 1
7 | PLASTERING & PAINTING WORKS
1 | External and internal plastering of 15mm thickness,with 1:4 mix ratio with wood float finish with fixing of all angulars of the Health Post as approved by engineer | M2 | 1131.68
2 | 2 coats of weather shield paint with base course (Wall putty) for exterior side and plastic emulsion paint with base course for enterior walls and provision of oil paint for facial board around roof as as approved by the engineer. | M2 | 1131.68
3 | 50mm thick cement/sand screed mix 1:3 | M2 | 182
4 | Supply and fix high quality ceramic tiles of 33x33cm width on floor screed for delivery room latrine | M2 | 182
5 | Supply and fix high quality ceramic tiles of 30x60cm on delivery room toilet walls with height of 2.2m | M2 | 12.1
8 | Other works and appliences
1 | Provision of toilet seat with flash, shower heads, washing basin, mirror, coat hangers, toilet paper hanger, soap holder, pipes and all other supplies for the three latrines | LS | 3
6.1 | Provide and fix all electericity equibment with nstallaion of ceiling mounted fan (60x60cm non-hanging fan) for all rooms and neon flouricent lights two in each room and four for the varanda with all switches, wires and sundries | LS | 1
4 | Add visibility in the size of 200cm x120cm well painted with the logos of the Funding agency and that of the implementor the with the year of the project as approved by an Engineer. | LS | 1
Total for construction of 1 unit of Health Post in Grible 2 |  |  |  |  | 0
B) BOQ for construction of twin latrines
# | Description | UNIT | Qty | Unit Price | Amount in USD
1 | SUBSTRUCTURE WORKS
1.1 | Excavate foundoutation trench (0.4m width x 0.5m depth x 25.4m length) | M3 | 4.56
2.1 | Mass concrete in 50 mm thick blinding layer (1:4:8 mix ) under the foundation wall (25.4m x 0.4m x 0.05m) | M3 | 0.456
3.1 | Rubble stone foundation wall in cement & sand mortar 1:4 ( 0.7m high x 0.4m wide x 22.8m length) 30 cm above ground level. | M3 | 6.16
4.1 | 200 mm thick stone hardcore filling well compacted and leveled (3.8x1.2+2x1.8x1.8)x0.2 | M3 | 2.208
Total Items For Substructure 1.0 |  |  |  |  | 0
2 | SUPER STRUCTURE WORK
1 | Rcc concrete (1:3:6 mix ) in conc. floor slab 70 mm thick with Re-bar R6 @ 300mm c/c. and overlaid 3cm cement sand screed, ensure the floor is sloping towards drop hole (3.8x1.2+2x1.8x1.8)x0.1m | M3 | 1.104
2 | Construction of 20cmx20cmx40cm CHBs walls up to door level (i.e. 2050mm above the foundation). Use 1:4 c/s mortar. Fill and level the top of walls. (4.2mx2.05mx3-3.2m2+1.8mx2.05mx3-0.5mx0.5mx2)+2.05mx1.2m) | M2 | 35.66
3 | provide and fix precast concrete on top of doors and wooden ventilations. Size is 1mx0.2mx0.15m. (1:2:3mix) with 3 No 12mm re-bars | No | 4
4 | Construction of 20cmx20cmx40cm CHBs slope-formation walls using 1:4 c/s mortar, over the precast beams.(0.5x4.2+0.8x4.2+3x(0.5x0.8x1.8) | M2 | 7.62
5 | R.C (1:2:4 mix) in No.1. top ring beam,( at top lintel ((4.2mx2+1.8mx2)x20cm x 15cm) with re-bars 4N0. Y12 & R6 links @ 250 mm c/c.Provide and fix 6mm iron strapping wires/roof -ties bedded in top ring beam to tie down the rafters. | M3 | 0.36
6 | Construct Toilet footrests by the size of 50cmx50cm, and at least 20cm high and install 6" delivery pipe @45degrees well as approved by the engineer | No | 2
Total Items For Super Structure 2.0
3 | ROOF WORK
1 | Fix 30 Gauge G.I.#30 iron sheets on 2” x 2” timber purling on 2”x3” timber rafters. Paint the roof with anti-rust paint, 2 coats | M2 | 17
2 | Construct timber fascia boards in the front, sides and back walls (i.e. under all eaves lines) and paint | ML | 10
Total Items For Roof Structure Work 3.0
1 | PLASTERING AND OTHER FINISHING WORKS
2 | External & internal plastering ,12 mm thick, cement / sand mix 1:3, with wood float finish. (7.62+35.66+0.36)x2 | M2 | 94.32
3 | Apply two coats white wash ( lime to white glue ratio =1:275) and distemper paint the plastered wall surface. | M2 | 94.32
Total Items For Plastering and Other Finishing Works 4.0
5 | DOORS AND WINDOWS WORK
1 | Supply and fix single leafed steel doors (No.s 2; 800x2050)mm, complete with frame, hinges & locks and to include two coats of gloss paint. | Pcs | 2
2 | Construct 450x450mm wooden ventlation grills as approved by the engineer | Pcs | 2
Total Items For Doors and Windows Work 5.0
6 | PIT LATRINE
1 | Excavation of the trench pit (1500x3000mm, depth= 4000mm). | M3 | 18
2 | Excavation of the ring beams foundation walls (10,600mmx0.4,depth= 1300mm). | M3 | 5.52
3 | Site clearance and aligning all the scattered hardcore excavated from the pit hall along the outside walls of the latrine to protect possible flooding entering into the latrine | LMS | 1
4 | Construction of 40cm thick stone masonry basement walls (1.3m deep) and 30cm above the groung level using 1:4 c/s mortar. Plaster the foundation wall | M3 | 6.78
5 | Construction of (3.8mx2.3mx150mm thick) R.CC cover slab provided with a (500 x 500mm) cleaning manhole or desludge opening. | M3 | 1.31
Total Items For Pit Latrine
7 | CONSTRUCTION OF HAND WASHING BASING
1 | Manhole, siphons and uPVC air pipes, sewerage system and installation of 2" of high pressure vent pipe 3m high with flyscreen. Fix vent pipe to the wall using 6mm dia bar. | LMS | 2
2 | Construction Hand washing Basin Blocks and connect to the pit latrine as per the design and connecting water from site water supply to the handwashing basin and latrines including water taps and sundries | LMS | 1
Total Items For Handwash facility |  |  |  |  | 0
8 | visibility for donor
1 | Paint visibility for Donor and the on the wall, the size is (1.2mx0.7m) as approved by the program | LMS | 1
Total Items For Visibility |  |  |  |  | 0
Total cost for twin latrine |  |  |  |  | 0
C) Elevated Water Tank
# | Description | UNIT | Qty | Unit Price | Amount in USD
1 | Excavate the foundation trenches for the basement walls. | M3 | 1.14
2 | Backfill the foundation trenches with dry stone ruble fill compact thoroughly and successively to satisfaction. Level the top of trenches at ground level with 1:5 c/s mortar to get ready for the construction of R.C. foundation beams | M3 | 1.14
3 | Construct the 400mm stone masonry short basement walls (ht.= 1350mm) using 1:5 c/s mortar. Level the top of walls to get ready for the construction of the pavement slab and ring beams. | M3 | 3.08
4 | Shutter, reinforce and concrete the 100mm R.C. pavement slab (reinforced with mesh D10mm @ 200mm centre both ways) and 150x400mm beams (reinforced with D12mm longitudinal bars and D6mm closed stirrups @200mm centre). | M3 | 1.01
5 | Construct 400mm Stone masonry water retaining walls (ht.= 1950mm) above the pavement slab using 1:4 mix cement mortar. Level the top of walls with 1:5 c/s mortar to get ready for the construction of the top 150mm ring beams. | M3 | 7.02
6 | Shutter, reinforce and concrete (1:2:4) the 150mm R.C. top ring beams (reinforced as the pavement slab ring beams). Insert D6mm m.s. U-shaped steel brackets in the fresh concrete to hold in position the roof trusses and rafters in case of strong winds. | M3 | 0.54
7 | Supply and fix 1½” G.I. inlet pipe using metal brackets to hold the pipe to the tank walls. Provide all necessary fittings assembly. | lms | 1
8 | Insert 1” G.I. outlet pipe with 1” T, 1” nipples, 1” union, 1” G.I. vertical air pipe and 1” end elbow. Provide all with the necessary fittings assembly. From the end of the elbow install 1” G.I. line to the back of the toilets, fix a 1”- ¾” reducer and ¾” lines through holes in the back wall to the toilets new ¾” taps . | lms | 1
9 | Insert 1” uPVC overflow pipe. | No | 1
10 | Insert 1” G.I. cleaning pipe provided with 1” G.I. gate valve. Provide all necessary fittings assembly. | lms
11 | Fix a pipe-wrangled stair. | lms | 1
12 | Connection of water to the delivery room latrine and the twin latrines including excavation and laying of 1" pipe with all fitting, foucets and technical labouR for laying the pipes in the three latrines | lms | 1
13 | Fix 32 Gauge G.I. sheets on 2”x2” timber purling on 1½”x3” timber trusses and rafters. Superpose sheets 200mm. Use only roofing nails for fixing the sheets, ensuring that the nails ate struck only on the raised ribs. | M2 | 7.02
14 | Construct in roof 500x500mm cleaning manhole provided with lifting eye, lid and lock. | No | 1
15 | Construct 25x200mm timber fascia boards under all eaves. Paint the fascia boards. | L.M. | 12.6
16 | Lay 40mm new screed on the pavement floor inside the tank topped by cement slurry finish sloping towards the cleaning pipe. | M2 | 3.42
17 | Render the tank’s internal walls in 20mm wood float cement plaster (mix 1:3) topped by cement slurry finish true to plumb. | M2 | 15.54
18 | Render the tank’s external water retaining walls 20mm steel float cement plaster (mix 1:4) true to plumb. | M2 | 22.26
19 | Render the vertical external faces of pavement ring beams, the underside of the pavement slab, and the ring beams in 12mm steel float cement plaster true to level and plumb. | M2 | 4.86
20 | Plaster the basement walls (ht.= 1350mm). | M2 | 17.55
21 | Paint the water retaining walls two coats water resistant paint. | M2 | 22.26
22 | Whitewash all the basement walls, the underside of pavement slab and ring beams and the vertical faces of the beams. | M2 | 22.41
23 | Paint the roof sheets two coats anti-rust high gloss paint. | M2 | 7.02
24 | Paint visibility for Donor and the on the wall, the size is (1.2mx0.7m) as approved by the | LMS | 1
Sub-Total for 6 M3 Water Tank in U.S. $
d) Perimeter walling
1 | Allow a provisiona sum for the construction of 100m perimeter walling from the excavation stage , substructures, superstructure with 15 concrete columns with d10 & d8 reinforcement bars. The height of the wall to be 3.0m ncluding all the plastering and 2 coats of painting. | SM | 300
2 | Allow provisonal sum for vehicular gate 4.0x3.0m with a proviosn of 1.2x2.4m high pedestrian gate all painted as per Engineers approval | Lms | 1
3 | Allow a provisional sum for 4 corner solar mounted lights - 150watts | No | 4
Total for the perimeter walling
e) Provisional sums
1 | Allow a provisional sum for 2.0x2.5.0x1.5 m placenta pit excavated and well finished with a concrete cover | No. | 1
2 | Allow a provisional sum for construction of 2.5x2.5m security room including all the works - substrsucture works, superstructure works and finishes to full approval by the engineer. | LS | 1
3 | Allow provisional sum for construction of an incinerator, 1.5x1.5m well finished with proper ventitllation to allow good fire combusion as shall be directed by engineer on site. | No. | 1
4 | Allow provisional sum for ground levelling and compaction | LS | 1
5 | Allow provisional sum for electrical works including all required accessories and the labor. | LS | 1
Total for provisonal sums
Grand-Total for Health Post with the support facility